## Master Tasks
Task ID | Phase | Module | Feature | Description | Priority | Dependencies | Acceptance Criteria | Status | Estimated Effort | Actual Effort | Developer Notes
FOUND-001 | Phase 0 | Repository | Project setup | Create monorepo structure, TypeScript, shared packages, environment strategy | P0 | None | Apps/packages/docs/planning structure works; typecheck passes | COMPLETED
FOUND-002 | Phase 0 | Backend | API foundation | Express app, config, logging, error handling, validation, API versioning | P0 | FOUND-001 | /api/v1 health endpoint works; standardized errors/logging | COMPLETED
DB-001 | Phase 0 | Database | MongoDB foundation | Mongoose connection, schemas conventions, indexes, migrations/seed strategy | P0 | FOUND-002 | MongoDB connection and schema/index conventions verified | COMPLETED
SEC-001 | Phase 1 | Security | Authentication | Secure registration/login, password hashing, access/refresh sessions | P0 | DB-001 | Auth flows secure and tested | COMPLETED
SEC-002 | Phase 1 | Security | RBAC | Organizations, memberships, roles and permissions | P0 | SEC-001 | Tenant isolation and authorization tests pass | COMPLETED
SEC-003 | Phase 1 | Security | Audit logging | Audit/security event infrastructure | P0 | SEC-002 | Sensitive actions create safe audit events | COMPLETED
CAT-001 | Phase 2 | Catalog | Categories | Category CRUD with organization isolation | P1 | SEC-002 | CRUD, validation, authorization and tests pass | COMPLETED
CAT-002 | Phase 2 | Catalog | Brands | Brand CRUD with organization isolation | P1 | SEC-002 | CRUD, validation, authorization and tests pass | COMPLETED
CAT-003 | Phase 2 | Catalog | Products | Product CRUD, media references, archive lifecycle | P1 | CAT-001,CAT-002 | Product lifecycle and permissions work | COMPLETED
CAT-004 | Phase 2 | Catalog | Variants | SKU, pricing, attributes and variant lifecycle | P1 | CAT-003 | Unique SKU and variant validation work | COMPLETED
INV-001 | Phase 3 | Inventory | Inventory engine | Locations, balances and immutable inventory transactions | P0 | CAT-004 | Stock changes are transaction-backed and auditable | COMPLETED
CUST-001 | Phase 4 | Customer | Customer accounts | Customer profile, addresses and account lifecycle | P1 | SEC-001 | Customer account flows work securely | COMPLETED
COM-001 | Phase 5 | Commerce | Wishlist | Wishlist and back-in-stock notification requests | P1 | CAT-004,CUST-001 | Out-of-stock variants can be saved and notifications requested | COMPLETED
COM-002 | Phase 5 | Commerce | Cart | Cart lifecycle and server-side pricing validation | P0 | INV-001,CUST-001 | Cart totals are server-authoritative | COMPLETED
COM-003 | Phase 5 | Commerce | Checkout | Checkout preview and order creation | P0 | COM-002 | Checkout validates stock, price and customer data | COMPLETED
COM-004 | Phase 5 | Commerce | Orders | Order lifecycle, tracking, cancellation and returns | P0 | COM-003 | State transitions are controlled and tested | NOT_STARTED
COM-005 | Phase 5 | Commerce | Payments | Payment provider abstraction and verified webhooks | P0 | COM-004 | Webhook verification/idempotency works | NOT_STARTED
COM-006 | Phase 5 | Commerce | Invoices | Invoice generation and customer access | P1 | COM-004 | Invoice snapshots and numbering work | NOT_STARTED
BUS-001 | Phase 6 | Business | Suppliers & purchases | Supplier management and purchase receiving | P1 | INV-001 | Receiving updates inventory through transaction engine | NOT_STARTED
BUS-002 | Phase 6 | Business | Expenses | Expense categories and expense lifecycle | P1 | SEC-003 | Expenses are auditable and organization-scoped | NOT_STARTED
BUS-003 | Phase 6 | Business | Ledger | Khatabook-like customer/supplier ledger | P0 | BUS-001,BUS-002 | Entries are balanced, auditable and traceable | NOT_STARTED
BUS-004 | Phase 6 | Business | POS & sales | Daily sales/POS recording and summaries | P1 | INV-001,BUS-003 | Sales reconcile to inventory and ledger | NOT_STARTED
BUS-005 | Phase 6 | Business | Employees & salary | Employee records and salary payments | P1 | BUS-003 | Salary records and payments are auditable | NOT_STARTED
BUS-006 | Phase 6 | Business | Investments | Business investments and withdrawals | P1 | BUS-003 | Investment movements reconcile to ledger | NOT_STARTED
RENT-001 | Phase 7 | Rental | Properties & rooms | Property, room and occupancy management | P1 | SEC-002 | Rooms and occupancy are organization-scoped | NOT_STARTED
RENT-002 | Phase 7 | Rental | Tenants | Tenant profiles, allocations and documents | P1 | RENT-001 | Allocation lifecycle and access control work | NOT_STARTED
RENT-003 | Phase 7 | Rental | Rent | Rent transactions and adjustments | P1 | RENT-002,BUS-003 | Rent transactions reconcile to ledger | NOT_STARTED
UTIL-001 | Phase 8 | Utilities | Electricity | Meter readings, bills and consumption | P2 | SEC-002 | Readings and bills are auditable | NOT_STARTED
UTIL-002 | Phase 8 | Utilities | Water | Meter readings, bills and consumption | P2 | SEC-002 | Readings and bills are auditable | NOT_STARTED
REP-001 | Phase 9 | Reporting | Dashboards | Admin dashboard and KPI summaries | P1 | BUS-004,BUS-005,UTIL-001,UTIL-002 | Dashboard data is permission-aware and performant | NOT_STARTED
REP-002 | Phase 9 | Reporting | Reports | Sales, inventory, finance, rental and utility reports | P1 | REP-001 | Reports are filtered by organization and date range | NOT_STARTED
MKT-001 | Phase 10 | Marketplace | Seller onboarding | Seller organizations, onboarding and seller roles | P2 | SEC-002 | Seller isolation and onboarding work | NOT_STARTED
MKT-002 | Phase 10 | Marketplace | Seller catalog | Seller-specific catalog, branding and pricing | P2 | MKT-001,CAT-004 | Seller catalog remains isolated | NOT_STARTED
MKT-003 | Phase 10 | Marketplace | Marketplace | Multi-vendor storefront, commissions and settlements foundation | P2 | MKT-002,COM-005 | Marketplace architecture is extensible and secure | NOT_STARTED