## Change Log
Change ID | Date | Task ID | Module | Change | Reason | Impact | Risk | Approved By | Git Commit
CHG-001 | 2026-09-11 | FOUND-002 | Backend | Implemented Express 5 API foundation (ESM/NodeNext): standardized response envelope, request ID, pino logging, zod-validated env config, CORS/helmet, in-memory rate-limit foundation, graceful shutdown, GET /api/v1/health. | Establish the backend platform foundation required before any business module (auth, catalog, commerce, etc.) can be built, per MASTER_TASK_LIST FOUND-002. | New apps/api runtime dependencies (Express, helmet, cors, pino, pino-http, zod, express-rate-limit); apps/api switched from CommonJS/Node16 to ESM/NodeNext; shared packages/config/eslint/base.mjs gained a no-unused-vars exception for underscore-prefixed params. | Low - foundation-only, no business logic, no DB/auth/RBAC. Rate limiter is single-instance only (documented, not yet wired to any route). | Developer (via this conversation) - plan approved across 3 rounds before execution | f0ff3a46bfc30b95aef0b6b0cf42d7e9adca4635
CHG-002 | 2026-09-11 | FOUND-001 | Planning | Corrected Planning/MASTER_TASK_LIST.xlsx Status column for FOUND-001 from NOT_STARTED to COMPLETED. | FOUND-001 was fully implemented, validated, and committed (commits d025c01, 7ffbc53) on 2026-09-10, but the Status column in MASTER_TASK_LIST.xlsx was never updated at completion time - only DEVELOPMENT_PROGRESS.xlsx was. Data-integrity correction, not a re-implementation. | Planning-data only; no code impact. | None - documentation/tracking correction. | Developer (via this conversation) | d025c01 (original FOUND-001 implementation); correction recorded alongside the FOUND-002 planning-docs commit
CHG-003 | 2026-09-12 | DB-001 | Database | Implemented MongoDB connection foundation: singleton Mongoose connection with bounded initial-connect retry, sanitizeFilter/strictQuery, dev-only autoIndex/autoCreate, global maxTimeMS plugin, withTransaction() helper (MongoDB-only), GET /api/v1/ready, production TLS/localhost startup safety guards. | Establish the database platform foundation required before any business schema (catalog, inventory, orders, etc.) can be built, per MASTER_TASK_LIST DB-001, extending FOUND-002 rather than redesigning it. | New apps/api dependencies (mongoose, mongodb-memory-server); apps/api/src/config/env.ts and index.ts modified to integrate DB connect/disconnect into the existing FOUND-002 boot/shutdown sequence; new GET /api/v1/ready endpoint and NOT_READY error code. | Low - foundation-only, no business schemas, no auth/RBAC, no Redis. withTransaction() explicitly documented as MongoDB-only, not atomic with external side effects. | Developer (via this conversation) - plan approved with 2 explicit confirmations before execution | 0ce5ed8786eebcefa7e37316d2d9f0b5c419745e
CHG-004 | 2026-09-12 | CAT-001 | Catalog | Implemented the Category domain foundation only: Mongoose model, repository, and service (Service -> Repository -> Model), organization-scoped hierarchy with cycle/cross-org prevention, soft-archive lifecycle, hand-rolled slug generation with database-enforced uniqueness. No HTTP routes/controllers, no Brand/Product/Variant. | Establish the Category foundation per MASTER_TASK_LIST CAT-001, without inventing a temporary authentication/authorization system while SEC-001/SEC-002 remain NOT_STARTED, and without broadening scope into CAT-002/003/004 territory (an earlier, broader combined-catalog proposal was explicitly rejected by the developer in favor of keeping the existing task boundaries intact). | New apps/api/src/modules/catalog/ directory (10 files, all new); no existing file modified; no new dependency; no route registered in app.ts/routes. | Low - foundation-only, no business CRUD exposed over HTTP yet, no auth/RBAC. Routes/controllers remain deferred until SEC-002. | Developer (via this conversation) - plan approved across 3 rounds (initial broad proposal rejected and narrowed, then the narrowed plan approved) before execution | b332de98c3133920a0c0626efb18309e6a2af2f3
CHG-005 | 2026-09-12 | CAT-002 | Catalog | Implemented the Brand domain foundation: Mongoose model, repository, and service (Service -> Repository -> Model), organization-scoped slug uniqueness, soft-archive lifecycle, logo reference (no upload/storage infrastructure). Extracted the shared isDuplicateKeyError() helper from CAT-001's category.repository.ts into apps/api/src/modules/catalog/lib/mongo-errors.ts, now used by both Category and Brand repositories. | Establish the Brand foundation per MASTER_TASK_LIST CAT-002, reusing CAT-001 conventions (slugify, common validation helpers, lifecycle enum shape) without inventing a temporary authentication/authorization system while SEC-001/SEC-002 remain NOT_STARTED. | New apps/api/src/modules/catalog/{lib/mongo-errors.ts+test, models/brand.model.ts, repositories/brand.repository.ts+test, services/brand.service.ts+test, validation/brand.schema.ts} (8 new files); catalog README.md extended with a Brand section; category.repository.ts modified only to import the extracted shared helper (Category behavior and tests unchanged, verified). No new dependency; no route registered. | Low - foundation-only, no business CRUD exposed over HTTP yet, no auth/RBAC. The category.repository.ts change is a pure, behavior-preserving extraction, confirmed by all pre-existing CAT-001 tests remaining green. | Developer (via this conversation) - plan approved with one required adjustment (shared mongo-errors extraction) before execution | 92af3b679a5bbfe2dbe08719d1161cfc755ebe12
CHG-006 | 2026-09-12 | SEC-001 | Security | Implemented the authentication foundation: hybrid short-lived JWT access token (jose, HS256) plus DB-backed opaque rotating refresh token (SecuritySession), atomic compare-and-swap refresh rotation with family-wide reuse-detection revocation, absolute + sliding session expiry, registration/login with no account-existence enumeration, progressive login-failure delay (not a hard lockout), session listing/revocation, authenticate and CSRF middleware, cookie-based transport. | Establish the authentication foundation per MASTER_TASK_LIST SEC-001, as the prerequisite for SEC-002 (RBAC/organizations) and every customer/business module that requires an authenticated actor - without building RBAC, MFA, password reset, email verification, GeoIP, Redis, or the SEC-003 audit framework prematurely. | New apps/api/src/modules/auth/ directory (18 files) plus apps/api/src/middleware/{authenticate.ts+test,csrf.ts+test} and apps/api/src/lib/cookies.ts+test (24 new files total); apps/api/src/config/env.ts, lib/http-errors.ts, types/express.d.ts, app.ts, routes/v1/index.ts, package.json, .env.example modified to wire in the new module; 3 new dependencies (jose, @node-rs/argon2, cookie); 4 pre-existing test files (env.test.ts, connection.test.ts, health.route.test.ts, ready.route.test.ts) updated only to supply the newly-required JWT_ACCESS_TOKEN_SECRET in their local test config. No apps/api/src/modules/catalog/ file touched. | Medium - this is the first module with real session/credential handling. Mitigated by: atomic (not read-then-write) refresh rotation proven by a dedicated concurrency test; family-wide revocation on reuse detection; generic, non-enumerating responses for every registration/login/refresh failure mode; progressive login delay instead of a lockout an attacker could weaponize against a victim; CSRF double-submit plus Origin/Referer validation; no plaintext secret ever logged (verified by a dedicated test). authenticate() intentionally performs no per-request DB lookup, a documented, accepted tradeoff for short-lived access tokens. | Developer (via this conversation) - plan approved after a revision round covering atomic rotation, session-family design, absolute lifetime, CSRF scope, registration/lockout behavior, and cookie-parsing verification, before execution | aaffd29
CHG-007 | 2026-09-13 | SEC-002 | Security | Implemented the RBAC foundation: Organization and OrganizationMembership (User has no organizationId), fixed OWNER/ADMIN/MEMBER roles with a static role-to-permission map (no Role/Permission collections), URL-based organization context re-verified server-side on every request via resolveOrganizationContext(), and atomic activeOwnerCount-based last-owner protection. Organization creation and the first OWNER membership are one atomic withTransaction() unit. | Establish the authorization foundation per MASTER_TASK_LIST SEC-002, as the prerequisite for tenant-scoped access to catalog and every future business module - without building RBAC UI, dynamic/custom roles, platform-admin functionality, or the SEC-003 audit framework prematurely. | New apps/api/src/modules/organizations/ directory (21 files); apps/api/src/lib/http-errors.ts (+FORBIDDEN/ForbiddenError) and apps/api/src/routes/v1/index.ts (mount /organizations) modified to wire in the new module. No new dependencies. No apps/api/src/modules/auth/, modules/catalog/, db/, or SEC-001 middleware/types file touched. | Medium - this is the first module enforcing cross-user/cross-organization access control. Mitigated by: a dedicated concurrency test proving the true write-skew race (two different owners demoted/removed concurrently) is correctly rejected by the atomic counter, not just a same-document race; an atomic bootstrap transaction with a rollback test; byte-identical generic 403s across all three organization-context failure reasons (no enumeration); and mass-assignment-proof membership creation (strict schema plus a service signature with no role/status parameter at all). Suspension has an accepted, deliberate limitation: no role, including OWNER, can reactivate a SUSPENDED organization within SEC-002 - by explicit instruction, not an oversight. | Developer (via this conversation) - plan approved after two revision rounds covering atomic bootstrap, last-owner concurrency strategy, the exact permission matrix, suspension semantics, membership lifecycle/indexing, mass-assignment protection, self-management edge cases, organization-context verification, and the req.membership/Express-declaration-merging approach, before execution | 358b2e2
CHG-008 | 2026-09-18 | SEC-003 | Security | Implemented the audit event infrastructure: a single append-only AuditEvent collection (no separate SecurityEvent), wired into the 13 sensitive actions verified reachable in the existing SEC-001 (auth) and SEC-002 (organizations) code. Audit writes for transactional operations happen strictly after commit, never inside a withTransaction() callback. Writes are best-effort and non-blocking. auth.login.failure never populates actorUserId/entityId. organization.reactivated is not instrumented since it cannot currently occur. | Establish the audit trail per MASTER_TASK_LIST SEC-003, satisfying "sensitive actions create safe audit events" for the security-domain actions that already exist, without inventing audit events for business modules (catalog, orders, payments) that have no route layer yet. | New apps/api/src/modules/audit/ directory (6 files); apps/api/src/modules/auth/services/auth.service.ts (+optional logger param on 5 functions, +13 audit calls) and routes/auth.route.ts (5 one-line edits); apps/api/src/modules/organizations/services/{organization,membership}.service.ts (+audit calls, no signature change). Additive-only test changes in 4 existing test files. No new dependencies. No modules/catalog, db/, middleware/authenticate.ts, middleware/csrf.ts, middleware/rate-limit.ts, or types/express.d.ts file touched. | Low-Medium - write-only infrastructure with no read/query surface yet, so no new attack surface for unauthorized data access. Mitigated by: audit writes placed after transaction commit (avoids duplicate records from MongoDB's transient-error retry), best-effort/non-blocking semantics (an audit outage cannot become a login/organization-mutation outage), three-layer metadata safety (scalar-only type, explicit per-call-site construction, forbidden-key runtime backstop) preventing secret leakage into audit records, and locked actor-omission semantics preventing a failed-login target from being misrepresented as a verified actor. | Developer (via this conversation) - plan approved after two revision rounds covering transaction timing, failed-login auditing and its coexistence with LoginAttempt, the exact locked action matrix (including explicitly excluding the unreachable organization.reactivated), the auth.service.ts call-graph inspection confirming the minimal optional-parameter change, metadata-safety mechanism, and tenant-context sourcing, before execution | b10e976
CHG-009 | 2026-09-18 | CAT-003 | Catalog | Implemented the Product domain foundation: Mongoose model, repository, and service (Service -> Repository -> Model, matching CAT-001/CAT-002 exactly), organization-scoped optional single categoryId and optional brandId references (both validated organization-scoped and non-archived, mirroring Category's own parent-validation pattern), optional media array (max 10 items), DRAFT/ACTIVE/ARCHIVED soft-archive lifecycle. No SKU, barcode, price, cost, inventory, or attributes - all explicitly Variant/CAT-004 responsibility. | Establish the Product foundation per MASTER_TASK_LIST CAT-003, reusing CAT-001/CAT-002 conventions (slugify, common validation helpers, lifecycle enum shape, cross-reference validation pattern) without prematurely building Variant (CAT-004), routes, or audit-event wiring. | New apps/api/src/modules/catalog/{models/product.model.ts, repositories/product.repository.ts+test, services/product.service.ts+test, validation/product.schema.ts} (6 new files); catalog README.md extended with a Product section. No existing CAT-001/CAT-002 file modified; no new dependency; no route registered; no audit event wired. | Low - foundation-only, no business logic exposed over HTTP yet, no auth/RBAC wiring, no audit integration. Category/Brand reference validation reuses an already-proven pattern (Category's own assertValidParent) rather than inventing a new one. Archiving a referenced Category/Brand never cascades onto an existing Product, verified by a dedicated test. | Developer (via this conversation) - plan approved with explicit locked decisions on categoryId/brandId optionality and cardinality, media shape/cap, archived-reference policy, and continued route/audit deferral, before execution | 0cb8ca2
CHG-010 | 2026-09-18 | CAT-004 | Catalog | Implemented the ProductVariant domain foundation: Mongoose model, repository, and service (Service -> Repository -> Model, matching CAT-001/002/003), required immutable productId reference validated like Product's own Category/Brand pattern, organization-scoped unique SKU (uppercase-normalized), optional organization-scoped unique barcode (partial index), integer-minor-unit pricing (price required, compareAtPrice/cost optional, per existing ADR-008), and a prototype-pollution-safe {key,value}[] attribute array capped at 30 items. DRAFT/ACTIVE/ARCHIVED lifecycle, unrestricted transitions for consistency with Category/Brand/Product. | Establish the ProductVariant foundation per MASTER_TASK_LIST CAT-004, adding the SKU/pricing/attribute/lifecycle layer CAT-003 deliberately excluded from Product, without inventing inventory, currency, variant media, or routes/audit infrastructure not required by this task. | New apps/api/src/modules/catalog/{models/product-variant.model.ts, repositories/product-variant.repository.ts+test, services/product-variant.service.ts+test, validation/product-variant.schema.ts} (6 new files); catalog README.md extended with a ProductVariant section. No existing CAT-001/CAT-002/CAT-003 file modified; no new dependency; no route registered; no audit event wired. | Low - foundation-only, no business logic exposed over HTTP yet, no auth/RBAC wiring, no audit integration. Product reference validation reuses an already-proven pattern (Product's own assertValidCategory/assertValidBrand) rather than inventing a new one. A barcode sparse-index approach was tried first, found not to behave as intended on a compound index (organizationId is always present, so sparse never excluded a barcode-less document), and corrected to a partialFilterExpression index before this was committed - caught by a failing test, not left as a known defect. | Developer (via this conversation) - plan approved with 12 explicit locked decisions on SKU/barcode/money/attribute/lifecycle/relationship/inventory/media/display-name/routes/audit design, plus two modifications (no digits-only/checksum barcode validation, no compareAtPrice>=price enforcement yet), before execution | b98a0ea
CHG-011 | 2026-09-18 | INV-001 | Inventory | Implemented the inventory engine: Location, StockBalance, and an append-only InventoryTransaction ledger. quantityOnHand is never directly patchable - only atomic incrementOrCreate/decrementIfSufficient operations exist, both requiring an active session. recordTransaction() handles PURCHASE/SALE/RETURN/ADJUSTMENT/DAMAGE/OPENING_BALANCE; a dedicated recordTransfer() atomically moves stock between two locations and writes matching TRANSFER_OUT/TRANSFER_IN entries, never via two independent recordTransaction() calls. | Establish the inventory foundation per MASTER_TASK_LIST INV-001, extending ADR-018's atomic-guarded-counter pattern to a new domain and reusing the append-only-collection pattern SEC-003 already established for AuditEvent, without prematurely building purchasing (BUS-001), POS (BUS-004), cart/checkout integration, pricing, currency, or SEC-003 audit wiring. | New apps/api/src/modules/inventory/ directory (18 files, all new). No existing CAT-001/002/003/004, auth, organizations, audit, db, or middleware file modified; no new dependency; no route registered; no audit event wired. | Medium - this is the first catalog-adjacent module requiring multi-document MongoDB transactions (ledger write + balance update must succeed or fail together) and the first requiring genuine concurrent-write correctness guarantees for a mutable aggregate. Mitigated by directly reusing ADR-018's already-proven atomic-guarded-decrement pattern rather than inventing a new one, and by two mandatory concurrency tests (concurrent initial-balance creation with no lost update, concurrent outbound operations with no negative balance) both passing against a real MongoDB replica set. A real defense-in-depth gap (a Mongoose custom validator silently not firing for an undefined ADJUSTMENT direction) was found and fixed during testing, not left as a known issue. | Developer (via this conversation) - plan approved after two revision rounds covering the Location/StockBalance/InventoryTransaction split, ADJUSTMENT direction semantics, the dedicated recordTransfer() operation, the atomic guarded-decrement requirement, mandatory concurrency test scenarios with exact numeric expectations, and explicit exclusion of audit wiring, forward-looking foreign keys, currency, and negative-inventory configuration, before execution | 95105c6
CHG-012 | 2026-09-19 | CUST-001 | Customer | Implemented Customer accounts: a global (non-organization-scoped) Customer profile 1:1 with User, and a separate Address collection supporting multiple addresses per customer with database-enforced at-most-one default billing/one default shipping via partial unique indexes. Added the first HTTP route layer outside SEC-001/SEC-002 (self-service /api/v1/customers/me... endpoints, identity always from req.auth.userId). setDefaultAddress runs inside one withTransaction(). | Establish the customer-account foundation per MASTER_TASK_LIST CUST-001, deliberately keeping Customer global (not organization-scoped) to match User's own precedent and the future marketplace direction, and adding routes now because the acceptance criterion ("Customer account flows work securely") is inherently a self-service HTTP flow, unlike the catalog/inventory foundation tasks. | New apps/api/src/modules/customers/ directory (17 new files); apps/api/src/routes/v1/index.ts modified only to mount the new router (2 hunks: import + router.use). No CAT-001-004, INV-001, auth, organizations, audit, or db file modified; no new dependency. | Medium - the first module to add a route layer since SEC-002, and the first to use a MongoDB transaction for a non-inventory purpose (default-address switching). Mitigated by: every route resolving identity exclusively from req.auth.userId (never a client-supplied id); every address repository function requiring customerId as a mandatory scoping parameter; a dedicated concurrency test proving two simultaneous setDefaultAddress calls resolve to exactly one default; a transaction-rollback test proving an archived-target default-swap attempt leaves the prior default untouched. One approved decision could not be fully implemented as specified: customer.archived/customer.restored audit events were approved but conflict with the explicit "do not modify SEC-003" boundary (wiring them requires extending SEC-003's own AUDIT_ACTIONS enum) - resolved by not touching SEC-003 and flagging the conflict explicitly (module README + a test proving the current zero-audit-event state) rather than silently choosing a side. | Developer (via this conversation) - plan approved after one revision round covering organization scope (global, not org-scoped), routes (approved now, self-service only), customer status (dedicated archive/restore only), address lifecycle (soft delete), the default-address transaction requirement (changed from two independent writes to one withTransaction() per explicit instruction), audit scope (customer.archived/restored only), and the country field (bounded free-text, no dependency), before execution | c3ab6a5
CHG-013 | 2026-09-19 | CUST-001 | Customer / Audit | Resolved DEC-007: extended SEC-003's AUDIT_ACTIONS/AUDIT_ENTITY_TYPES with customer.archived, customer.restored, and Customer (an 8-line additive change to modules/audit/models/audit-event.model.ts, no existing action/entity/behavior touched). Wired archiveCustomerProfile()/restoreCustomerProfile() to call the existing audit.service.ts record() after a successful archive/restore, with actorUserId from the authenticated userId and entityId the Customer._id. | CUST-001's approved audit requirement (customer.archived/customer.restored) directly conflicted with that same task's "do not modify SEC-003" boundary. The conflict was recorded (DEC-007) rather than resolved unilaterally; the developer subsequently approved the small additive SEC-003 extension as the resolution. | Modified apps/api/src/modules/audit/models/audit-event.model.ts (+8 lines: two new AUDIT_ACTIONS entries, one new AUDIT_ENTITY_TYPES entry, one explanatory comment). Modified apps/api/src/modules/customers/services/customer.service.ts (audit wiring in archiveCustomerProfile/restoreCustomerProfile, optional trailing logger parameter added to both) and apps/api/src/modules/customers/routes/customer.route.ts (logger passthrough on DELETE /me). No other SEC-003 file modified (repository, service internals, error handling, metadata rules all unchanged). No CAT-001-004, INV-001, auth, or organizations file touched. | Low - purely additive to a locked enum, with the existing best-effort/non-blocking audit.service.ts record() reused unchanged. Mitigated by: 5 new/rewritten tests proving exactly one customer.archived/customer.restored event per successful operation with the correct actorUserId/entityType/entityId, zero events for ordinary profile/address CRUD, and zero events for a failed (NotFoundError) archive/restore attempt; SEC-003's own 12 existing tests re-run in isolation and confirmed unaffected; full regression (CAT-001-004, INV-001, auth, organizations) re-verified unchanged. | Developer (via this conversation) - explicit approval of the small additive SEC-003 extension as the resolution to DEC-007, with 13 numbered requirements (exact actions to add, no SEC-003 redesign, actor/entity source, no new audit API, no CRUD/address-lifecycle auditing) specified before execution | a7656f9
CHG-014 | 2026-09-19 | COM-001 | Commerce | Implemented Wishlist and BackInStockRequest: two separate collections referencing a global Customer and an organization-owned ProductVariant. Partial unique indexes ({customerId,variantId} scoped to status:ACTIVE, {customerId,variantId,status} scoped to status:PENDING) permit re-adding/re-requesting after soft-removal/cancellation while preventing duplicates while active. Back-in-stock requests require aggregate stock (all locations) to be zero, checked via INV-001's existing repository, unmodified. Added the second self-service HTTP route layer (after CUST-001). | Establish the wishlist/back-in-stock foundation per MASTER_TASK_LIST COM-001, deliberately stopping at "saved and requested" per the task's own acceptance wording - no notification delivery (DEC-003/DEC-004 unresolved, no queue infrastructure) and no FULFILLED/fulfillment-detection logic (would require modifying INV-001 or inventing job infrastructure). | New apps/api/src/modules/wishlist/ directory (18 new files); apps/api/src/routes/v1/index.ts modified only to mount the new router. No CAT-001-004, INV-001, CUST-001, auth, organizations, audit, or db file modified; no new dependency. | Medium - the first module to validate an organization reference without using SEC-002's membership middleware (a new, deliberately narrower read-only existence+ACTIVE check was needed, since customers are not organization members), and the first to layer a cross-collection stock aggregation read (INV-001) underneath a create-time validation rule. Mitigated by: the authoritative tenant check remaining ProductVariant's own organization-scoped lookup, never the client-supplied organizationId alone; concurrent-create race tests for both partial unique indexes; all four required multi-location stock scenarios tested explicitly. One real regression was found and fixed during validation, not left as a known issue: the wishlist router's initially-blanket authenticate() middleware incorrectly 401'd genuinely unmatched, unrelated routes (caught by the pre-existing health.route.test.ts regression test), corrected by scoping the middleware to the router's own two path prefixes before this task was considered complete. | Developer (via this conversation) - plan approved after one revision round, then implementation approved with 24 numbered requirements covering organization-scoping validation flow, customer-identity resolution, both partial-unique-index designs with mandatory re-add/re-request and concurrency tests, multi-location stock semantics with four explicit test scenarios, archived-variant/archived-customer write-blocking, route shape and request bodies, cross-module reuse boundaries, and explicit exclusion of FULFILLED/notification-delivery/SEC-003 audit wiring, before execution | 183c87d
CHG-015 | 2026-09-19 | COM-002 | Commerce | Implemented Cart and CartItem: one Cart per (customerId, organizationId), CartItem as a separate, hard-deleted collection carrying only {cartId, organizationId, variantId, quantity} - no price/name/SKU snapshot. Every price/subtotal/total in GET /cart is resolved live from the current ProductVariant/Product on every call. The 1..9999 per-item quantity ceiling is enforced entirely inside a single atomic MongoDB operation (filter-embedded ceiling check + $inc + upsert), never a read-calculate-write sequence. GET and the clear-cart operation never create a Cart; only POST /cart/items does (via an atomic findOrCreate). | Establish the Cart foundation per MASTER_TASK_LIST COM-002 ("Cart lifecycle and server-side pricing validation," acceptance: "Cart totals are server-authoritative"), reusing COM-001's read-only organization/variant validation pattern and INV-001's unmodified stock-balance read for an informational availability indicator, without inventing inventory reservation, discount/tax/shipping calculation, or a Cart lifecycle/status field beyond what this task requires. | New apps/api/src/modules/cart/ directory (14 new files); apps/api/src/routes/v1/index.ts modified only to mount the new router under a '/cart' prefix. No CAT-001-004, INV-001, CUST-001, COM-001, auth, organizations, audit, or db file modified; no new dependency. | Medium - the first module in this codebase to enforce a numeric ceiling atomically inside a single upsert-increment MongoDB operation rather than a separate read-then-write step (mitigated by two dedicated concurrency race tests: 5000+5000 exceeding 9999 resolves to exactly one success, 3000+3000 staying within it applies both), and the first CartItem-style collection to use a hard delete plus a plain (non-partial) unique index instead of this codebase's usual soft-delete-with-partial-index pattern (a deliberate, reasoned deviation, not an oversight, since a cart item has no history value once removed). CartItem carries no customerId (unlike WishlistItem/BackInStockRequest), so item-level ownership is resolved via a two-step cartId-then-Cart.customerId check rather than a single-collection scoped query - proven safe by dedicated cross-customer IDOR tests at the service and route layers. | Developer (via this conversation) - plan approved after a detailed 30-section repository audit, then implementation approved with explicit mandatory corrections: the 9999 ceiling enforced atomically (with 9990+9/9990+20 required test scenarios), GET must never create a Cart, and archived-variant handling specified per-operation (POST/PATCH reject, DELETE always allowed, GET shows flagged) - before execution | 5a0639f
CHG-016 | 2026-09-19 | COM-003 | Commerce | Implemented Checkout preview/confirm and a new minimal orders module: Order {customerId, organizationId, items[] embedded snapshot, subtotal, total, status: PENDING_PAYMENT, shippingAddress/billingAddress embedded snapshot}. Preview and confirm share one pricing/validation function that always re-resolves current ProductVariant.price/Product.name and validates aggregate StockBalance (read-only, INV-001 unmodified). Order creation and Cart clearing happen inside one withTransaction(), re-reading Cart/CartItem via the transaction's own session by importing COM-002's public Cart/CartItem models directly (their repositories do not accept a session, and COM-002 is closed). | Establish the Checkout foundation per MASTER_TASK_LIST COM-003 ("Checkout preview and order creation," acceptance: "Checkout validates stock, price and customer data"), taking the roadmap's own wording literally so COM-003, not COM-004, creates the first Order - COM-004 ("Order lifecycle, tracking, cancellation and returns") is scoped to managing an already-existing order's state machine, not creating one. | New apps/api/src/modules/checkout/ (9 files) and apps/api/src/modules/orders/ (5 files), all new; apps/api/src/routes/v1/index.ts modified only to mount the new router under /checkout. No CAT-001-004, INV-001, CUST-001, COM-001, COM-002, auth, organizations, audit, or db file modified; no new dependency. | Medium-high - the first module to open a MongoDB transaction whose read step (re-reading Cart/CartItem via the session) reaches into another, already-closed module's Mongoose models directly rather than through that module's own repository layer, specifically because COM-002's repositories do not accept a ClientSession and modifying a closed module was out of scope. Mitigated by: read+delete only (never a write of new Cart data), documented explicitly in both modules' READMEs, and proven safe by a genuine concurrent-confirm race test (two simultaneous confirms for the same cart resolve to exactly one Order, the loser correctly seeing an empty cart via MongoDB's own write-conflict-plus-retry behavior - no bespoke idempotency-key infrastructure needed for that specific race). A second, separate, explicitly-flagged risk: a client retry after a lost HTTP response following a successful commit will see an empty cart rather than being replayed the original order - a known, deliberately deferred limitation, not a silently accepted one. | Developer (via this conversation) - plan approved after a detailed 35-section repository audit that surfaced and required an explicit ruling on a tension in the roadmap's own wording (whether COM-003 or COM-004 creates the initial Order), then implementation approved with 3 core invariants stated as non-negotiable (server-authoritative price/totals, inventory validation without mutation, atomic Order-creation-plus-Cart-clearing) plus detailed, mandatory address/pricing/transaction/concurrency requirements, before execution | 9bd3bfe
CHG-017 | 2026-10-10 | COM-004 | Commerce | Implemented COM-004 Tranche A: Order lifecycle state machine (PENDING_PAYMENT -> CONFIRMED -> PROCESSING -> PACKED -> SHIPPED -> DELIVERED, plus CANCELLED from PENDING_PAYMENT/CONFIRMED only), every transition enforced by an atomically-guarded findOneAndUpdate (filter embeds the required fromStatus, never read-then-write); customer order list/detail/cancel APIs; tracking fields (carrier, trackingNumber, shippedAt, deliveredAt); a new returns module (ReturnRequest, customer-only create/list, backed by a dedicated ReturnRequestLock collection that serializes concurrent submissions against the same order via MongoDB write-conflict detection plus automatic transaction retry). SEC-003's AuditEvent additively extended with order.status_changed, order.cancelled, return.requested. During the mandatory post-implementation security review, finding F-1 (HIGH) was identified: a single return-request payload repeating the same variantId bypassed the purchased-quantity/cumulative-quantity invariant, since both the Order-snapshot check and the in-transaction cumulative check validated each item entry independently instead of by aggregate. Remediated with schema-level duplicate-variantId rejection plus independent service-layer per-variant quantity aggregation (defense-in-depth, not reliance on schema validation alone), 4 new regression tests, and a subsequent independent follow-up security review that returned PASS with no new findings. | Establish the Order lifecycle required by COM-004's own MASTER_TASK_LIST acceptance criterion ("State transitions are controlled and tested"), with returns modeled as a separate ReturnRequest collection rather than an Order.status value, per the approved plan. F-1 was remediated because a financial/inventory-integrity invariant must not rely solely on schema validation, per explicit developer requirement. | New apps/api/src/modules/returns/ module (models, repositories, service, validation, README); apps/api/src/modules/orders/ extended (model, repository, service, validation, route, README); apps/api/src/modules/audit/models/audit-event.model.ts additively extended (3 new AUDIT_ACTIONS, 2 new AUDIT_ENTITY_TYPES); apps/api/src/routes/v1/index.ts modified only to mount the orders router. No CAT-001-004, INV-001, CUST-001, COM-001, COM-002, COM-003 checkout files, auth, organizations, or db file modified; no new dependency. 139 new tests across the implementation and the F-1 remediation (891/891 total passing, zero regression). | Medium - the first insert-based (not update/delete-based) multi-document invariant in this codebase: MongoDB transaction isolation does not naturally serialize two concurrent transactions that each insert a different new document, so ReturnRequestLock (one document per orderId, atomically upserted inside the transaction before the aggregate read) was introduced to force write-conflict detection and automatic retry - proven by dedicated concurrency tests. The HIGH-severity F-1 finding was caught by the mandatory security review before this Planning entry was ever recorded, fixed, and independently re-verified PASS - consistent with the explicit instruction that Planning/completion records be held back until the security-review workflow passes. Tranche B (staff/admin order management, payment/refund integration, inventory decrement, return-window enforcement, return approve/reject/receive) remains open; COM-004 is recorded as IN_PROGRESS, not COMPLETED, in MASTER_TASK_LIST.xlsx. | Developer (via this conversation) - Tranche A scope, the ReturnRequestLock concurrency design, and explicit SEC-003 action names approved before implementation; the F-1 remediation scope and required defense-in-depth approach approved separately after the initial security review returned BLOCKED; this closure recorded after an independent follow-up security review returned PASS | 5af12bd (Tranche A implementation), 43d1af1 (F-1 remediation)